## 消费电子产品结构设计流程

Master Review

3D Review

Tooling Review

Prototype Review

3D Modify

3D Modify

3D Modify

Tooling Quotation

Vendor Selection

ID Mockup

Total 97 Working Days

6 Working Days

1 Working Day

15 Working Days

1 Working Day

1 Working Day

6 Working Days

1 Working Day

1 Working Day

1 Working Day

2 Working Days

Initial Layout *

PD/ ID *

Lab Phone

Phone Layout *

Master [Version Control] *

BOM/ PCBA/ ME Spec *

Review Minutes/Change List *

Design Manual

3D File [Version Control] *

PCB Layout *

ME BOM/ Part Number *

Review Minutes/Change List *

3D Review Check List *

Machine Phone Housing

Tooling Quotation *

Review Minutes/Change List *

2D Drawing/Spec *

Tooling Review Minutes

Tooling Contract *

Tooling Schedule

Material Selection

DRN */Drawing Release

ID

PID

Detail Design

Prototyping

ME 2D

ID finalization

Duration

Deliverables

Tooling

T1 Eva.

T2 Eva.

T0 Review

Tooling Modify

T1 Review

Tooling Modify

T2 Review

Tooling Modify

25 Working Days

1 Working Day

3 Working Days

1 working day

7 Working Days

1 working day

4 Working Days

1 Working Day

7 Working Days

1 Working Day

4 Working Days

1 Working Day

5 Working Days

1 Working Day

6 Working Days

4 Working Days

Full Dimensions Report

2D Drawing

Issue List

ME Follow-up List*

Housing Sample/Transparent

Painted Sample

Full Dimensions Report *

ME Evaluation report*

MEALT Report

Review Minutes/issue List

DRN/ICN/Drawing Release

Housing Sample/Transparent

Full Dimension Report *

ME Evaluation report*

Pilot Run Report *

ALT Report

Issue List */Review Minutes

DRN/ICN/Drawing Release

Housing Sample/Transparent

Full Dimension Report *

Painted Sample

Evaluation Report *

Pilot Run Report

Golden Sample

Golden Painted Sample

Issue List *

CQR

SA Check List

T2

T1

T3

Qualification

SA

2K Pilot